## Mutual Group Project
Project Name | Mutual Group-Project
Phase Name | Owner | Start Date | End Date | Completed Date | Open Tasks | Closed Tasks
Initiation Phase | Prashant Kumar | 2024-03-21 | 2024-04-05 | 2024-04-05 | 0 | 9
Assessment Phase | Prashant Kumar | 2024-04-06 | 2024-05-06 | 2024-05-06 | 0 | 3
Implementation and execution | Prashant Kumar | 2024-05-07 | 2024-09-24 | 2024-09-24 | 0 | 16
Testing and Validation | Prashant Kumar | 2024-09-25 | 2024-10-09 | 2024-10-09 | 0 | 3
Project Closer Phase | Prashant Kumar | 2024-10-10 | 2024-10-16 | 2024-10-16 | 0 | 4
Formulas:
End Date = [Start Date]+15
Start Date = [End Date, row above]+1

## Mutual Group P-PRJ-729
Phase Name | Task List Name | Task Name | Start Date | Due Date | Owner | Project Name | Project ID | Project Status
Project Prerequisite and Initiation | Project Prerequisite Milestone | Signed SoW | 2024-03-21 | 2024-03-21 | Pravin Mishra | Mutual Group- Project | PRJ-729 | Completed
|  | Project Revenue Details | 2024-03-21 | 2024-03-21 | Pravin Mishra | Mutual Group- Project | PRJ-729 | Completed
|  | GDC Estimation (Cost and Work hours) | 2024-03-21 | 2024-03-21 | Pravin Mishra | Mutual Group- Project | PRJ-729 | Completed
|  | BOQ | 2024-03-21 | 2024-03-21 | Pravin Mishra | Mutual Group- Project | PRJ-729 | Completed
|  | Solutioning document(Proposed Design which is mapped to customer requirements) | 2024-03-21 | 2024-03-21 | Pravin Mishra | Mutual Group- Project | PRJ-729 | Completed
|  | Stakeholder details | 2024-03-22 | 2024-03-23 | Pravin Mishra | Mutual Group- Project | PRJ-729 | Completed
| Initiation | Internal Kick Off | 2024-03-24 | 2024-03-25 | Ashutosh Thakur, Pratap Rathaur, Pravin Mishra | Mutual Group- Project | PRJ-729 | Completed
|  | Project Kick Off | 2024-03-29 | 2024-03-29 | Ashutosh Thakur, Pratap Rathaur, Pravin Mishra | Mutual Group- Project | PRJ-729 | Completed
|  | Azure Subscription Onboarding | 2024-03-30 | 2025-04-05 | Ashutosh Thakur, Pratap Rathaur, Pravin Mishra | Mutual Group- Project | PRJ-729 | Completed
Assessment | Assess | Pre-Req Details | 2025-04-06 | 2025-04-13 | Prashant Kumar | Mutual Group- Project | PRJ-729 | Completed
|  | Information Gathering sessions | 2025-04-14 | 2025-04-26 | Prashant Kumar | Mutual Group- Project | PRJ-729 | Completed
|  | Assessment of oracle data sources and approach finalization | 2025-04-27 | 2025-05-06 | Prashant Kumar | Mutual Group- Project | PRJ-729 | Completed
Execution | Dev Setup | Set up Synapse Workspace | 2025-04-07 | 2025-04-11 | Ashutosh Thakur, Lalit Kumar, Srishti Budholia | Mutual Group- Project | PRJ-729 | Completed
|  | Create and Validate Linked Services for All Data Source | 2025-04-12 | 2025-04-25 | Ashutosh Thakur, Lalit Kumar, Srishti Budholia | Mutual Group- Project | PRJ-729 | Completed
|  | Setup ADLS | 2025-04-26 | 2025-05-08 | Ashutosh Thakur, Lalit Kumar, Srishti Budholia | Mutual Group- Project | PRJ-729 | Completed
|  | Develop Synapse pipeline for Full load and Incremental Load for DWH tables | 2025-05-09 | 2025-06-08 | Ashutosh Thakur, Lalit Kumar, Srishti Budholia | Mutual Group- Project | PRJ-729 | Completed
|  | Design data type handling logic and logging in the pipeline | 2025-06-09 | 2025-06-15 | Ashutosh Thakur, Lalit Kumar, Srishti Budholia | Mutual Group- Project | PRJ-729 | Completed
|  | Create DDL for all tables with converting data type in dedicated sql pool | 2025-06-16 | 2025-06-30 | Ashutosh Thakur, Lalit Kumar, Srishti Budholia | Mutual Group- Project | PRJ-729 | Completed
|  | Create metadata driven table | 2025-07-01 | 2025-07-08 | Ashutosh Thakur, Lalit Kumar, Srishti Budholia | Mutual Group- Project | PRJ-729 | Completed
| Dev | Load Data into ADLS | 2025-07-09 | 2025-07-13 | Ashutosh Thakur, Lalit Kumar, Srishti Budholia | Mutual Group- Project | PRJ-729 | Completed
|  | Load Data into Dedicated sql pool | 2025-07-14 | 2025-07-18 | Ashutosh Thakur, Lalit Kumar, Srishti Budholia | Mutual Group- Project | PRJ-729 | Completed
|  | Troubleshooting call for Data mapping | 2025-07-19 | 2025-07-23 | Ashutosh Thakur, Lalit Kumar, Srishti Budholia | Mutual Group- Project | PRJ-729 | Completed
| Replicate to PROD and Test | Extract Pipeline ARM templates | 2025-07-24 | 2025-07-28 | Ashutosh Thakur, Lalit Kumar, Srishti Budholia | Mutual Group- Project | PRJ-729 | Completed
|  | Create Pipelines using ARM in Test and PROD | 2025-07-29 | 2025-08-02 | Ashutosh Thakur, Lalit Kumar, Srishti Budholia | Mutual Group- Project | PRJ-729 | Completed
|  | Mapping data source and linked services | 2025-08-03 | 2025-08-07 | Ashutosh Thakur, Lalit Kumar, Srishti Budholia | Mutual Group- Project | PRJ-729 | Completed
| Powerbi | Business Logic for Power BI | 2025-08-08 | 2025-08-12 | Ashutosh Thakur, Lalit Kumar, Srishti Budholia | Mutual Group- Project | PRJ-729 | Completed
|  | Power BI report creation | 2025-08-13 | 2025-08-17 | Ashutosh Thakur, Lalit Kumar, Srishti Budholia | Mutual Group- Project | PRJ-729 | Completed
|  | Publish the power BI report | 2025-08-18 | 2024-09-24 | Ashutosh Thakur, Lalit Kumar, Srishti Budholia | Mutual Group- Project | PRJ-729 | Completed
Testing and Validation | Prod | Test full load and incremental load | 2024-09-25 | 2024-09-30 | Ashutosh Thakur, Lalit Kumar, Srishti Budholia | Mutual Group- Project | PRJ-729 | Completed
|  | Data Validation | 2024-10-01 | 2024-10-03 | Ashutosh Thakur, Lalit Kumar, Srishti Budholia | Mutual Group- Project | PRJ-729 | Completed
|  | Power BI Report Validation | 2024-10-04 | 2024-10-09 | Ashutosh Thakur, Lalit Kumar, Srishti Budholia | Mutual Group- Project | PRJ-729 | Completed
Project Closer Phase | Transition ,Handover & Sign Off | Create Build and Deployment Document | 2024-10-10 | 2024-10-13 | Ashutosh Thakur, Pratap Rathaur, Pravin Mishra | Mutual Group- Project | PRJ-729 | Completed
|  | Provide all required documents for handover | 2024-10-14 | 2024-10-14 | Ashutosh Thakur, Pratap Rathaur, Pravin Mishra | Mutual Group- Project | PRJ-729 | Completed
|  | Transition Workshop | 2024-10-15 | 2024-10-15 | Ashutosh Thakur, Pratap Rathaur, Pravin Mishra | Mutual Group- Project | PRJ-729 | Completed
|  | Project Sign off | 2024-10-16 | 2024-10-16 | Pravin Mishra | Mutual Group- Project | PRJ-729 | Completed
Formulas:
Start Date = [Due Date, row above]+1
Start Date = [Start Date, row above]+1
Due Date = [Start Date]+1